## RANGE
| "F A C E S H E ET" |  |  | $M |  | IDENTIFIABLES |  | PROJECT OR STUDY |  |  |  | WILMINGTON EQUIPMENT |  |  |  | $M | IDENTIFIABLE INSTRUMENTS |  |  |  | $M
[17 empty] | ANALYZERS |  |  |  | 750
WILMINGTON EQUIPMENT |  |  |  | 16653.52 |  | 4.2305 | 70451.9872 | NAME : | F. L. ARBOGAST |  |  | EQUIPMENT |  |  |  | 16013 | DCS |  |  |  | 1575
MISC. EQUIPMENT |  |  | 5.1 | 849.3295
[17 empty] | 100 | 105 |  | T O T A L ===> | 2341.275
|  |  | PROCESS EQUIPMENT====> | 17502.8495 |  |  |  | CHARGE NO. : | [8 empty] | Min | Max |  |  | 1.007
INSTALL. | 1.512 | 5.934 | 4.008 | 2073.3445 | [12 empty] | IDENTIFIABLE ELECTRIC |  |  |  | $M
FIELD ERECTED EQUIPMENT |  |  |  | 0 |  | 3.3867 | 0 | PLANT : | CORPUS CHRISTI | [7 empty] | SUBSTA, DIESEL GEN, COMMUN, ETC. |  |  |  | 1284
FOUND., SUPPORTS, & PLATFORMS |  |  | 7.007 | 1226.4247 |  |  |  | DEPARTMENT : | CHEMICALS
|  |  | INSTALLED EQUIPMENT===> | 20802.6187 |  |  |  | ESTIMATE | [8 empty] | 100 | 105 |  | T O T A L ===> | 1325.088
[17 empty] | Min | Max |  |  | 1.032
P | IPE |  | 47.088 | 9795.5371 |  |  |  | PREPARED BY:
I | NSTRUMENTS |  | 21.67 | 4507.9275 |  |  |  | DATE | 2005-02-15 | [7 empty] | EXISTING EQUIPMENT |  |  |  | $M
E | LECTRIC |  | 9.054 | 1883.4691 | [12 empty] | EXISTING SPHERES |  |  |  | 400
IDENTIFIABLE PIPE |  |  |  | 2392.58 |  | 1.9046 | 4557.0169 | LETTER
IDENTIFIABLE INSTRUMENTS |  |  |  | 2341.275 |  | 1.9046 | 4459.2991 | SCOPE | [8 empty] | 100 | 100 |  | T O T A L ===> | -400
IDENTIFIABLE ELECTRIC |  |  |  | 1325.088 |  | 1.9046 | 2523.823 | BY : | W. E. GUENTHNER | [7 empty] | Min | Max |  |  | 1
CONTROL EQUIPMENT |  |  | 0 | 0 |  |  |  | DATE :
EXISTING EQUIPMENT |  |  |  | -400 |  | 1.9046 | -761.8582 | CASE DESCRIPTION : | [8 empty] | SPECIAL PROCESS EQUIPMENT |  |  |  | $M
[17 empty] | REFRIGERATION EQUIPMENT |  |  |  | 994
|  |  | SUB TOTAL=====> | 42648.4953 |  |  |  | FREON ALTERNATIVES MFG
SPECIAL PROCESS EQUIPMENT |  |  |  | 1032.766 |  | 1.9046 | 1967.0532 | FACILITY - HFC-134a WEST | [8 empty] | 100 | 105 |  | T O T A L ===> | 1032.766
OTHER EQUIPMENT |  |  |  | 337.644 |  | 1.9046 | 643.0922 | HIGH TEMPERATURE PROCESS | [8 empty] | Min | Max |  |  | 1.039
BUILDINGS AND STRUCTURES |  |  |  | 3192.16 |  | 1.9046 | 6079.9334 | VGA FILE - CDEWEG01:#10
IDENTIFIABLE PGS FACILITIES |  |  |  | 0 |  | 1.9046 | 0 | S. F.==> |  | 1 | [6 empty] | OTHER EQUIPMENT |  |  |  | $M
[17 empty] | PACKING |  |  |  | 332
|  |  | SUB TOTAL=====> | 47211.0653 |  |  |  | X RATIO=> |  | 1
[17 empty] | 100 | 105 |  | T O T A L ===> | 337.644
MISCELLANEOUS PGS |  |  | 0 | 0 | [12 empty] | Min | Max |  |  | 1.017
D & R |  |  | 0.1978 | 93.3835 |  |  |  |  | PCR 20
MAINTAINING PRODUCTION |  |  | 0 | 0 |  |  |  | PROJECT COST, M$ | [8 empty] | BUILDINGS AND STRUCTURES |  |  |  | $M
[12 empty] | 100 | 110 |  | T O T A L ===> | 16653.52 | BUILD & STRUCT |  |  |  | 2003
|  |  | SUB TOTAL=> | 47304.4488 | [7 empty] | Min | Max |  |  | 1.04 | ARCH & CIVIL WORK |  |  |  | 807
| BARE LABOR = | 27.8538 | [5 empty] | ---->>---------->>------->>----project level L A B O R -------->> | 24.9056 | 22701.5277
| WILM. MATERIAL = | 50.59 | [5 empty] | -------->>- project level WILMINGTON MATERIAL ---->> | 31.5017 | 28713.9143 |  | FIELD ERECTED EQUIPMENT |  |  |  | $M | 100 | 125 |  | T O T A L ===> | 3192.16
| FIELD MATERIAL = | 21.5562 | [5 empty] | -------->>--------->>- project level FIELD MATERIAL ------->> | 18.2436 | 16629.0885 |  | F/E EQUIPMENT |  |  |  |  | Min | Max |  |  | 1.136
WORKING CONDITIONS |  |  | 0.993 | 130.8386 | [12 empty] | IDENTIFIABLE PGS FACILITIES |  |  |  | $M
FREIGHT AND TAXES |  |  | 12.883 | 4396.7559 | [12 empty] | IDENT PGS FACIL
FIELD DIRECTS |  |  | 10.03 | 4744.6362 | [7 empty] | 100 | 105 |  | T O T A L ===> | 0
[12 empty] | Min | Max |  |  | 1.028
|  |  | SUB TOTAL=====> | 56576.6795 | [12 empty] | 100 | 105 |  | T O T A L ===> | 0
CONTINGENCY |  |  | 0 | 0 | [7 empty] | IDENTIFIABLE PIPE |  |  |  | $M | Min | Max |  |  | 1.018
IDENT PIPE
|  |  | NET TOTAL===> | 56576.6795 | [7 empty] | OSOH/OSUG PIPE & INSUL |  |  |  | 2108 | SPARES AND PORTABLES |  |  |  | $M
PREMIUM TIME |  |  | 2.3782 | 1345.5117 | [12 empty] | SPARES & PORT |  |  |  | 690
MINOR CHANGES |  |  | 3.063 | 1732.9437 | [12 empty] | EWO'S & TEMP CONSTR FACIL |  |  |  | 510
[12 empty] | 100 | 125 |  | T O T A L ===> | 2392.58 | 100 | 105 |  | T O T A L ===> | 1230
|  |  | SUB TOTAL=====> | 59655.1349 | [7 empty] | Min | Max |  |  | 1.135 | Min | Max |  |  | 1.025
ESCALATION |  | 226.982 | 188.374 | 12226.557 | #REF!
|  |  | DIRECT TOTAL==> | 71881.6919
ENGINEERING & HOME OFFICE |  |  | 20.1059 | 14452.4773 |  |  |  | ->>------->>------->>--- E & H O --->> | 15.8556 | 14452.4773 |  |  | Step #1 | [5 empty] | Excel Calculation to be Manual
FIELD INDIRECTS |  |  | 3.968 | 2852.2655 |  |  |  | --------->>-FIELD INDIRECTS -->> | 3.9344 | 3586.1776 |  |  | Calculate with Blank (space bar) to get Total with fixed input | [5 empty] | with one interation only
CONTRACT ADMINISTRATION |  |  | 1.021 | 733.9121 |  |  |  | -->>----->>- C O N T R A C T S -->> | 5.5591 | 5067.1614 |  |  | Calculate with T and then B to get the Extreme values
SPARES & PORTABLES |  |  |  | 1230 |  | 1 | 1230 | [5 empty] | Extremes
|  |  | SUB TOTAL=====> | 91150.3467 | [7 empty] | T= | 93990.5259 | 16.1639
LIPS ADJ | ----->GUESS -----> |  | 0 | 0 | [8 empty] | 80912.0155 |  |  |  | Step #2 |  |  | Step #3
|  |  | PROJECT GRAND TOTAL===> | 91150.3467 |  | 1 | 91150.3467 |  | 100 | 91150.3467 |  | B= | 77301.612 | 4.4621 |  |  | Set to |  |  | Calculate Multiple Times
[17 empty] | Zero 1st, |  |  | with "Y" in L73
|  |  |  | E A R L Y P R O J E C T A N A L Y S I S S Y S T E M | [8 empty] | (flat)=0, 5=(triangular) |  |  |  | Calculate,
|  |  |  | D A T A I N P U T S H E E T F O R R A N G E E S T I M A T E | [5 empty] | Blank, Y, B or T |  |  | 5 | High Squeeze |  | "Bang" is | Then Set to
[10 empty] | Y | RANGE % |  | 5 | Low Squeeze |  | within | Equal to |  | Segment Values
I N T E R N A L F A C T O R S | [5 empty] | F A C E S H E E T F A C T O R S |  |  |  | Factor | Min | Max | TriDist |  |  | Segments | Column A | A | Low | High | Ave.
INSULATION LABOR |  |  |  | 50 |  | MISCELLANEOUS EQUIPMENT |  |  | 5.1 | 5 | 95 | 105 | 1.02 |  | 1 |  | 7 | 7 | 77301.612 | 78136.0577 | 77718.8348 | 0.1402 |  | 0
FNDS, SUPP, & PLTFRMS. LAB. |  |  |  | 50 |  | EQUIP. INSTALL. FIELD MATERIAL |  |  | 1.512 | 1.5 | 95 | 105 | 1.008 |  | 2 |  | 11 | 11 | 78136.0577 | 78970.5034 | 78553.2805 | 0.3605 |  | 0
PIPE LABOR |  |  |  | 50 |  | EQUIPMENT INSTALLATION LABOR |  |  | 5.934 | 6 | 95 | 105 | 0.989 |  | 3 |  | 56 | 56 | 78970.5034 | 79804.9491 | 79387.7262 | 1.4821 |  | 0
PIPE FIELD MATERIAL |  |  |  | 50 |  | EQUIPMENT INSULATION |  |  | 4.008 | 4 | 95 | 105 | 1.002 |  | 4 |  | 81 | 81 | 79804.9491 | 80639.3947 | 80222.1719 | 3.1043 |  | 0
INSTRUMENT LABOR |  |  |  | 20 |  | FOUNDS., SUPPORTS & PLATFORMS |  |  | 7.007 | 7 | 95 | 105 | 1.001 |  | 5 |  | 164 | 164 | 80639.3947 | 81473.8404 | 81056.6176 | 6.3889 |  | 0
INSTRUMENT FIELD MATERIAL |  |  |  | 15 |  | P I P E (L & M) |  |  | 47.088 | 48 | 95 | 105 | 0.981 |  | 6 |  | 263 | 263 | 81473.8404 | 82308.2861 | 81891.0633 | 11.6563 | Lo | 263
ELECTRICAL LABOR |  |  |  | 45 |  | I N S T R U M E N T (L & M) |  |  | 21.67 | 22 | 95 | 105 | 0.985 |  | 7 |  | 412 | 412 | 82308.2861 | 83142.7318 | 82725.509 | 19.9079 |  | 412
ELECTRICAL FIELD MATERIAL |  |  |  | 30 |  | ELECTRIC (L & M) |  |  | 9.054 | 9 | 95 | 105 | 1.006 |  | 8 |  | 496 | 496 | 83142.7318 | 83977.1775 | 83559.9547 | 29.8418 |  | 496
SPECIAL PROCESS ITEMS LABOR |  |  |  | 40 |  | CONTROL EQUIPMENT (L & M) |  |  | 0 | 0 | 95 | 105 | 0.995 |  | 9 |  | 593 | 593 | 83977.1775 | 84811.6232 | 84394.4004 | 41.7184 |  | 593
SPECIAL PROC. FIELD MATERIAL |  |  |  | 15 |  | MISCELLANEOUS PGS (L & M) |  |  | 0 | 0 | 95 | 105 | 0.993 |  | 10 |  | 624 | 624 | 84811.6232 | 85646.0689 | 85228.8461 | 54.205 | Max | 624
OTHER ITEMS LABOR |  |  |  | 40 |  | D & R (L & M) |  |  | 0.1978 | 0.2 | 95 | 105 | 0.989 |  | 11 |  | 585 | 585 | 85646.0689 | 86480.5146 | 86063.2918 | 65.9191 |  | 585
OTHER ITEMS FIELD MATERIAL |  |  |  | 15 |  | MAINTAINING PRODUCTION (L & M) |  |  | 0 | 0 | 95 | 105 | 1.002 |  | 12 |  | 508 | 508 | 86480.5146 | 87314.9603 | 86897.7375 | 76.0913 |  | 508
BUILDINGS & STRUCTURES LABOR |  |  |  | 50 |  | WORKING CONDITIONS (L & M) |  |  | 0.993 | 1 | 95 | 105 | 0.993 |  | 13 |  | 430 | 430 | 87314.9603 | 88149.406 | 87732.1832 | 84.7016 |  | 430
BUILD. & STRUCT. FIELD MATERIAL |  |  |  | 20 |  | FREIGHT & TAXES (L & M) |  |  | 12.883 | 13 | 95 | 105 | 0.991 |  | 14 |  | 307 | 307 | 88149.406 | 88983.8517 | 88566.6289 | 90.849 |  | 307
IDENTIFIABLE PGS LABOR |  |  |  | 40 |  | FIELD DIRECTS (L & M) |  |  | 10.03 | 10 | 95 | 105 | 1.003 |  | 15 |  | 192 | 192 | 88983.8517 | 89818.2974 | 89401.0746 | 94.6936 | Hi | 192
IDENT. PGS FIELD MATERIAL |  |  |  | 25 |  | C O N T I N G E N C Y |  |  | 0 | 0 | 95 | 105 | 0.987 |  | 16 |  | 136 | 136 | 89818.2974 | 90652.7431 | 90235.5203 | 97.4169 |  | 0
MISCELLANEOUS PGS LABOR |  |  |  | 40 |  | PREMIUM TIME (LABOR) |  |  | 2.3782 | 2.3782 | 95 | 105 | 1 |  | 17 | Bang | 70 | 71 | 90652.7431 | 91487.1888 | 91069.966 | 98.8186 |  | 0
MISC. PGS FIELD MATERIAL |  |  |  | 25 |  | MINOR CHANGES (L & M) |  |  | 3.063 | 3 | 95 | 105 | 1.021 |  | 18 |  | 37 | 37 | 91487.1888 | 92321.6345 | 91904.4117 | 99.5595 |  | 0
D & R LABOR |  |  |  | 85 |  | M P C I N D E X |  |  | 226.982 | 217 | 95 | 105 | 1.046 |  | 19 |  | 17 | 17 | 92321.6345 | 93156.0802 | 92738.8574 | 99.8999 |  | 0
D & R FIELD MATERIAL |  |  |  | 15 |  | CURRENT I N D E X |  |  | 188.374 | 194 | 95 | 105 | 0.971 |  | 20 |  | 5 | 5 | 93156.0802 | 93990.5259 | 93573.3031 | 100 |  | 0
MAINTAINING PRODUCTION LABOR |  |  |  | 50 |  | ENGINEERING & HOME OFFICE |  |  | 20.1059 | 19.6731 | 95 | 105 | 1.022
MAINT. PROD. FIELD MATERIAL |  |  |  | 50 |  | F I E L D I N D I R E C T S |  |  | 3.968 | 4 | 95 | 105 | 0.992 |  |  |  | 4994 | 4995 | [5 empty] | 4410
MINOR CHANGES LABOR |  |  |  | 50 |  | CONTRACT ADMINISTRATION |  |  | 1.021 | 1 | 95 | 105 | 1.021
MINOR CHANGES FIELD MATERIAL |  |  |  | 50 |  | L I P S A D J U S T M E N T |  |  | 0 | 0 | 95 | 105 | 1.001
% LABOR & F/M IN L/S CONTRACT |  |  |  | 80
% WILM. MATL. IN L/S CONTRACT |  |  |  | 15 | [14 empty] | 91150.3467 | = Total
[19 empty] | 85423.0043 | = Most Likely
[21 empty] | 85423.0043 | 40 | Max
[21 empty] | 85423.0043 | 624
[21 empty] | 81151.854 | 0 | Lo
[21 empty] | 81151.854 | 263
[21 empty] | 89694.1545 | 0 | Hi
[21 empty] | 89694.1545 | 192
The Probability is
88.2883
The Total will be
5
of the Most likely Total